## IPTT
|  | Quarterly Targets |  |  |  | Q1 |  | Q2 |  | Q3 |  | Q4 |  | Quarterly Results |  |  |  | FY26
Results Heirachy | Performance Indicators | Q1 Target | Q2 Target | Q3 Target | Q4 Target | Planned Budget | Budget Expense | Planned Budget | Budget Expense | Planned Budget | Budget Expense | Planned Budget | Budget Expense | Q1 Results | Q2 Results | Q3 Results | Q4 Results | FY26 Budget | FY26 Target | FY26 Results | Planned Budget/Output | Budget Expense/Output
Goal: To contribute to improvement in social-economic wellbeing among vulnerable individuals and households in Uganda, Northern Karamoja
Outcome 1: Increased income among women and girls.
Ouput 1.1: Improved soil and water conservation practices adopted | 1.1.1: Number of farmers trained on Zai pits and moisture conservation | 98 | 99 | 98 | 99 | 301450.5999 | 301411 | 301450.5999 |  | 301450.5999 |  | 246250 |  | 96 |  |  |  | 1150601.7996 | 394 | 96 | 39140087.7996 | 301411
| 1.1.2: Number of Zai pit demonstration plots established |  | 295 | 99 |  |  |  | 13250810 |  | 284350 | [7 empty] | 13535160 | 394 | 0
| 1.1.3: Number of farmers who have established climate-smart vegetable gardens |  | 296 | 98 |  |  |  | 814950 |  | 246250 | [7 empty] | 1061200 | 394 | 0
| 1.1.4: Number of farmers trained on the construction and use of water harvesting and irrigation systems |  |  | 99 | 295 |  |  |  |  | 22654376 |  | 738750 | [5 empty] | 23393126 | 394 | 0
Output 1.1b: Increased access to agricultural inputs and production support | 1.1b.1: Number of farmers who received quality seeds | 394 |  |  |  | 11072068 | 8876068 | [10 empty] | 11072068 | 394 | 0 | 11072068 | 8876068
Output 1.1c: Improved farmer capacity in agribusiness and enterprise development | 1.1c.1: Number of BSPs and staff trained on farmer business curriculum | 20 |  |  |  | 2425000 | 2078600 | [6 empty] | 9 |  |  |  | 2425000 | 20 | 9 | 16152000 | 10139436
| 1.1c.2: Number of farmers trained on farming as a business by BSPs | 59 | 236 | 236 | 177 | 1173000 | 1434000 | 2072000 |  | 1116000 |  | 1366000 |  | 68 |  |  |  | 5727000 | 708 | 68
| 1.1c.3: Number of youth trained on enterprise selection and management | 113 | 112 | 113 | 112 | 6649250 | 6626836 | 441250 |  | 468250 |  | 441250 |  | 104 |  |  |  | 8000000 | 450 | 104
Output 1.2: Improved post-harvest handling, drying, and storage practices | 1.2.1: Number of farmers trained on improved drying, storage, and handling techniques |  | 152 | 304 | 152 |  |  | 1179000 |  | 1280000 |  | 593000 | [5 empty] | 3052000 | 608 | 0 | 6067000 | 0
| 1.2.2: Number of farmer groups trained on cereal, pulse, vegetable processing and food preservation for value addition |  | 87 | 261 | 261 |  |  | 405000 |  | 1275000 |  | 1335000 | [5 empty] | 3015000 | 608 | 0
Output 1.3: Improved household income through diversified and well-managed agribusiness enterprises | 1.3.1: Number of households trained on improved chicken husbandry, feeding, housing, and disease control | 177 | 177 | 177 | 177 | 910000 | 569083 | 910000 |  | 877000 |  | 850000 |  | 161 |  |  |  | 3547000 | 708 | 161 | 12101488 | 2042607
| 1.3.2: Number of beneficiaries trained on poultry business management and record keeping | 15 | 15 | 15 | 15 | 107500 | 107500 | 37500 |  | 37500 |  | 37500 |  | 15 |  |  |  | 220000 | 60 | 15
| 1.3.3: Number of VSLA groups supported by DDS-NK | 3 | 3 | 8 | 4 | 1506492 | 27000 | 27000 |  | 54000 |  | 27000 |  | 3 |  |  |  | 1614492 | 18 | 3
| 1.3.4: Number of groups mentored on basic skills for making local skirts and beads for income generation | 5 | 4 | 5 | 4 | 1679999 | 1339024 | 1679999 |  | 1679999 |  | 1679999 | [5 empty] | 6719996 | 18 | 0
Output 1.4: Improved market access and business linkages | 1.4.1: Number of farmers participating in market exposure visits and buyer-seller meetings |  | 8 | 4 | 6 |  |  | 720600 |  | 376800 |  | 370800 | [5 empty] | 1468200 | 18 | 0 | 1995200 | 0
| 1.4.2: Number of producers linked to markets, input suppliers, veterinary services, agro-dealers, and buyers | 2 | 6 | 6 | 6 | 44000 | 0 | 219000 |  | 132000 |  | 132000 |  | 15 |  |  |  | 527000 | 20 | 15
Outcome 2: Strengthened participation of women and girls in decision making
Output 2.1: Improved community awareness and prevention of Gender Equality, Disability and Social Inclusion (GEDSI) barriers and Gender-Based Violence (GBV) | 2.1.1: Number of community members reached through dialogues and sensitization sessions on GEDSI and GBV prevention | 150 | 150 | 150 | 150 | 990500 | 833700 | 1950500 |  | 1934000 |  | 1855000 |  | 159 |  |  |  | 6730000 | 600 | 159 | 19687000 | 2255200
| 2.1.2: Number of faith leaders trained and engaged to integrate GEDSI and GBV prevention messages in preaching and community interactions | 19 | 55 | 57 | 57 | 850000 | 680000 | 2550000 |  | 2550000 |  | 2550000 |  | 138 |  |  |  | 8500000 | 188 | 138
| 2.1.3: Number of adolescents reached through awareness sessions on GEDSI principles and GBV prevention, including rights, reporting, and referral pathways | 150 | 150 | 150 | 150 | 588500 | 402000 | 588500 |  | 395000 |  | 395000 |  | 71 |  |  |  | 1967000 | 600 | 71
| 2.1.4: Number of community members reached through GEDSI and GBV awareness dialogues conducted during market days | 125 | 125 | 125 | 125 | 372500 | 339500 | 372500 |  | 312500 |  | 312500 |  | 148 |  |  |  | 1370000 | 500 | 148
| 2.1.5: Number of community members reached through campaigns using meetings, IEC materials, and media on GEDSI and GBV prevention |  | 250 |  | 250 |  |  | 560000 |  |  |  | 560000 | [5 empty] | 1120000 | 500 | 0
Output 2.1a: Strengthened coordinated youth engagement and violence prevention mechanisms through community-based approaches (CBIM) | 2.1a.1: Number of out-of-school boys and girls reached through Community-Based Integrated Model (CBIM) activities using sports, agriculture, and other engagement methods |  | 125 | 250 | 125 |  |  | 288500 |  | 550000 |  | 261500 | [5 empty] | 1100000 | 500 | 0 | 6168500 | 0
| 2.1a.2: Number of stakeholders engaged in joint planning and design of youth violence prevention interventions under CBIM |  |  | 27 | 27 |  |  | 903500 |  | 454000 |  | 454000 | [5 empty] | 1811500 | 600 | 0
| 2.1a.3: | [8 empty] | 1628500 |  | 1628500 | [5 empty] | 3257000 |  | 0
Output 2.2: Strengthened leadership, participation, and decision-making capacity of women and girls in households and communities | 2.2.1: Number of women and girls trained on leadership and decision-making skills for household and community roles |  | 13 | 13 | 24 |  |  | 305000 |  | 305000 |  | 583000 | [5 empty] | 1193000 | 50 | 0 | 4629200 | 1049000
| 2.2.2: Number of male champions recognized and promoted for supporting women’s leadership and equitable decision-making in households and communities |  | 13 | 26 | 11 |  |  | 378100 |  | 560000 |  | 378100 | [5 empty] | 1316200 | 50 | 0
| 2.2.3: Number of women and girls supported to participate in Women’s Day and 16 Days of Activism events to practice leadership and advocate for gender equality | 10 |  |  | 10 | 1060000 | 1049000 |  |  |  |  | 1060000 |  | 10 |  |  |  | 2120000 | 20 | 10
Output 2.3: Improved access to SRH and social inclusion services | 2.3.1: Number of beneficiaries referred to the health facility for SRH services |  | 10 | 10 |  |  |  | 211500 |  | 238500 | [7 empty] | 450000 | 20 | 0 | 504000 | 0
| 2.3.2: Number of PWDs linked to appropriate service providers to ensure access to assistive devices that enhance |  |  | 20 | [5 empty] | 54000 | [7 empty] | 54000 | 20 | 0
Outcome 3: Increased adoption of sustainable natural resource management
Output 3.1: Strengthened community-based disaster preparedness, climate resilience, and environmental governance structures | 3.1.1: Number of Village Disaster Management (VDM) and regreening committees trained and supported to coordinate climate-resilient activities |  | 125 | 250 | 125 |  |  | 355000 |  | 590000 |  | 295000 | [5 empty] | 1240000 | 500 | 0 | 16544000 | 873210
| 3.1.2: Number of Village Disaster Management (VDM) and regreening committees supported to develop disaster preparedness and regreening action plans | 60 | 180 | 180 | 180 | 1040000 | 873210 | 3720000 |  | 3120000 |  | 3120000 | [5 empty] | 11000000 | 600 | 0
| 3.1.3: Number of committee members trained on disaster risk management (DRM), climate-smart natural resource management (NRM), early warning systems (EWS), and community advocacy |  | 125 | 250 | 125 |  |  | 517000 |  | 1007000 |  | 490000 |  | 60 |  |  |  | 2014000 | 500 | 60
| 3.1.4 Number of DRM committee memebsr facilitated to participate in performance review meetings |  | 125 | 250 | 125 |  |  | 572500 |  | 1145000 |  | 572500 | [5 empty] | 2290000 |  | 0
Output 3.2: Improved sustainable land use and forest management practices for enhanced environmental conservation and climate resilience | 3.2.1: Number of farmers supported to establish and maintain nurseries for seedlings through farmer groups and youth clubs | 99 | 98 | 99 | 98 | 367736.5 | 232000 | 307736.5 |  | 367736.5 |  | 307736.5 |  | 99 |  |  |  | 1350946 |  | 99 | 3975026 | 0
| 3.2.2: Number of community members trained on sustainable land and forest management |  | 99 | 98 | 197 |  |  | 425080 |  | 397000 |  | 794000 | [5 empty] | 1616080 | 394 | 0
| 3.2.3 Number of community members reached through community tree planting campaigns |  | 197 | 99 | 98 |  |  | 504000 |  | 197000 |  | 307000 | [5 empty] | 1008000 |  | 0
3.3: Increased community awareness and adoption of clean and sustainable energy solutions | 3.3.1: Number of households trained on briquette production and use |  | 99 | 197 | 98 |  |  | 290500 |  | 537500 |  | 247000 | [5 empty] | 1075000 | 394 | 0 | 12986000 | 0
| 3.3.2: Number of community members reached through awareness campaigns on clean energy benefits |  | 197 |  | 197 |  |  | 93000 |  |  |  | 93000 | [5 empty] | 186000 | 394 | 0
| 3.3.3: Number of community members trained on installation, safe use, and maintenance of clean energy stoves |  | 197 | 99 | 98 |  |  | 8862500 |  | 1431250 |  | 1431250 | [5 empty] | 11725000 |  | 0
4. Monitoring, Evaluation and Learning Activities | 4.1.1: Number of technical monthly monitorings conducted | 1 | 3 | 3 | 3 | 288000 | 244400 | 864000 |  | 864000 |  | 864000 | [5 empty] | 2880000 |  | 0 | 19871180
| 4.1.2: Number of quaterly Joint district monitoring with the sectorial technical personnel conducted | 1 | 1 | 1 | 1 | 1212375 | 0 | 1212375 |  | 1212375 |  | 1212375 | [5 empty] | 4849500 |  | 0
| 4.1.3 Number of people participating during quarterly implementation review meetings | 48 | 48 | 48 | 48 | 2172000 | 2463500 | 2172000 |  | 2172000 |  | 2172000 |  | 34 |  |  |  | 8688000 |  | 34
| 4.1.4: Number of project groups profiled |  | 18 |  |  |  |  | 1327500 | [9 empty] | 1327500 |  | 0
| 4.1.5: Number of Output data tracking and documentation conducted |  | 2 | 1 | 1 | 531545 | 0 | 531545 |  | 531545 |  | 531545 | [5 empty] | 2126180 |  | 0

## Q1 Output Dash_Board
FY26 | Output 1.1: Increased access to climate-smart agricultural production and water management | Output 1.1b: Increased access to agricultural inputs and production support |  | Output 1.1c: Improved farmer capacity in agribusiness and enterprise development
Output 1.3: Improved household income through diversified and well-managed agribusiness enterprises |  |  |  |  | Output 1.4: Improved market access and business linkages
| Output 2.1: Improved community awareness and prevention of Gender Equality, Disability and Social Inclusion (GEDSI) barriers and Gender-Based Violence (GBV) |  |  |  | Output 2.2: Strengthened leadership, participation, and decision-making capacity of women and girls in households and communities
Output 3.1: Strengthened community-based disaster preparedness, climate resilience, and environmental governance structures |  |  | Output 3.2: Improved sustainable land use and forest management practices for enhanced environmental conservation and climate resilience |  |  | 4. Monitoring, Evaluation and Learning Activities

## Finance Q1
FY 26 | PLANNED BUDGET VS EXPENSE
Output 1.1: Increased access to climate-smart agricultural production and water management |  | Output 1.1b: Increased access to agricultural inputs and production support | Output 1.1c: Improved farmer capacity in agribusiness and enterprise development
Output 1.3: Improved household income through diversified and well-managed agribusiness enterprises |  | Output 1.4: Improved market access and business linkages | Output 2.1: Improved community awareness and prevention of Gender Equality, Disability and Social Inclusion (GEDSI) barriers and Gender-Based Violence (GBV)
Output 2.2: Strengthened leadership, participation, and decision-making capacity of women and girls in households and communities |  | Output 3.1: Strengthened community-based disaster preparedness, climate resilience, and environmental governance structures |  | Output 3.2: Improved sustainable land use and forest management practices for enhanced environmental conservation and climate resilience
4. Monitoring, Evaluation and Learning Activities

## Sheet4
FY26 | Output 1.1: Increased access to climate-smart agricultural production and water management |  | Output 1.2: Improved post-harvest handling, drying, and storage practices |  |  | Output 2.1a: Strengthened coordinated youth engagement and violence prevention mechanisms through community-based approaches (CBIM)
Output 1.1c: Improved farmer capacity in agribusiness and enterprise development |  | Output 1.3: Improved household income through diversified and well-managed agribusiness enterprises |  |  | Output 2.2: Strengthened leadership, participation, and decision-making capacity of women and girls in households and communities
Output 1.4: Improved market access and business linkages |  | Output 2.1: Improved community awareness and prevention of Gender Equality, Disability and Social Inclusion (GEDSI) barriers and Gender-Based Violence (GBV) |  |  | Output 2.3: Improved access to SRH and social inclusion services
Output 3.1: Strengthened community-based disaster preparedness, climate resilience, and environmental governance structures |  | Output 3.2: Improved sustainable land use and forest management practices for enhanced environmental conservation and climate resilience |  | 3.3: Increased community awareness and adoption of clean and sustainable energy solutions